## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-08-04 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Mr.Chathura Ms.Shashika , Ms.Irasha, Ms.Dilanthika |  | 1. Review the project plan & schedule. | 1hour
|  | Testing |  |  | 2. Agreed to complete testing phase 2 of 'System Configuration' module on 6th of August.
3.Agree to complete module testing on 15th of August & Start integration testing.
|  | Project Enhancements |  |  | 4. Agree to complete 'Employee Online Leave Appliction' module on 8th of August.
5. Decide to Include 'View Roster Assignments' module to the project & project plan.
6. Decide to add personalization module to the home page.
7. Decide to maintain cost/profit centere details in 'Employee Information Management' module including from cost/profit center & to cost/profit center details in 'Employee Transfer' module.
|  | Demonstration |  |  | 8.Decide to prepare the presentaion & fixed the Demonstration date.
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
| 1.Agreed to complete testing phase 2 of 'System Configuration' module on 6th of August. | Ms.Dilanthika & Ms.Irasha | 2014-08-04 | 2014-08-06 |  |  |  | Done.
| 2.Agree to complete module testing on 15th of August & Start integration testing. | Ms.Dilanthika & Ms.Irasha | 2014-08-04 | 2014-08-15
| 3.Agree to complete 'Employee Online Leave Appliction' module on 8th of August. | Mr.Thanuja | 2014-08-04 | 2014-08-08
| 4.Decide to Include 'View Roster Assignments' module to the project & project plan. | Mr.Pramodya | 2014-08-04 |  |  |  |  | Done.
| 5. Decide to add personalization module to the home page. | Mr.Thanuja | 2014-08-04
| 6.Decide to prepare the presentaion & fixed the Demonstration date. | Mr.Anjana | [5 empty] | Done.
Action Items