## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-09-04 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Ms.Shashika , Ms.Irasha, Ms.Dilanthika | Mr.Chathura | 1.Decided to complete all modules & testing on or before 12/09/2014 | 1hour
2.Decided to complete attendance machine integration on or before 12/09/2014
3.Decided to complete integration testing within 15/09/2014 - 19/09/2014
4.Decided to complete UI fine tuning within 15/09/2014 - 09/09/2014
5.Decided to complete UAT within 22/09/2014 - 25/09/2014
6.Decided to complete data configuration on 26/09/2014
7.Decided to Launch HRIS on 01/10/2014
8.Decided to complete Documentations (first phase) : Finalize SRS – 12/10/2014 Start Lessons Learned – 22/09/2014 Discuss User Manual format
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
1 | Decided to complete all modules & testing on or before 12/09/2014 | Mr.Anjana Mr.Thanuja Mr.Pramodya
2 | Decided to complete attendance machine integration on or before 12/09/2014 | Mr.Anjana
3 | Decided to complete integration testing within 15/09/2014 - 19/09/2014 | Ms.Irasha Ms.Dilanthika
4 | Decided to complete UI fine tuning within 15/09/2014 - 09/09/2014 | Mr.Anjana Mr.Thanuja Mr.Pramodya
5 | Decided to complete UAT within 22/09/2014 - 25/09/2014 | HR Dept.
6 | 8.Decided to complete Documentations (first phase) Finalize SRS – 12/10/2014 Start Lessons Learned – 22/09/2014 Discuss User Manual format | Mr.Anjana Mr.Thanuja Mr.Pramodya Mrs.Irasha Mrs.Dilanthika
Action Items