## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-07-11 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Ms.Shashika , Ms.Irasha, Ms.Dilanthika | Mr.Chathura | 1. Review the project plan & schedule. | 1hour
2. Agree to rectify the bug – “Once enter key pressed in some fields, system is automatically logged out."
3. Decide to initiate documenting lessons learned.
4. Agree to test DB tables along with interfaces.
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
| Agree to rectify the bug – “Once enter key pressed in some fields, system is automatically logged out." | Thanuja | 2014-07-11
| Decide to initiate documenting lessons learned. |  | 2014-07-11
| Agree to test DB tables along with interfaces. | Irasha & Dilanthika | 2014-07-11
Action Items