## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-09-11 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Mr.Chathura, Ms.Irasha, Ms.Dilanthika |  | 1.Decided to complete summarizing on 15/09/2014 | 1hour
2.Decided to complete 'Leave Management' module on 12/09/2014
3.Decided to complete 'Salary' module on 11/09/2014
4.Decided to complete 'Roster Management' module on 15/09/2014
6.Decided to start integration testing on 16/09/2014
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
1 | Decided to complete summarizing on 15/09/2014 | Mr.Thanuja
2 | Decided to complete 'Leave Management' module on 12/09/2014 | Mr.Anjana
3 | Decided to complete 'Salary' module on 11/09/2014 | Mr.Chathura
4 | Decided to complete 'Roster Management' module on 15/09/2014 | Mr.Pramodya
5 | Decided to start integration testing on 16/09/2014 | Ms.Irasha Ms.Dilanthika
Action Items