## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-08-04 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Ms.Shashika , Ms.Irasha, Ms.Dilanthika | Mr.Chathura | 1.Review the project plan & schedule. | 1hour
2.Agree to hold review meeting every Friday 10-11.
|  | Testing |  |  | 3.Decided to finalized module testing on 31st of August.
|  | Project Enhancements |  |  | 4.Agree to complete 'Online Leave Application' form on 18th of August.
5.Agree to complete 'Leave Management' module on 20th of August.
6.Decided to finalized 'Salary Module' by 18th of August.
7.Discussed regarding attendance integration with system.
|  | Demonstration |  |  | 8.Decided to demonstrate the system functionality to QA Team.
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
1 | Decided to finalize module testing on 31st of August. | Ms.Dilanthika & Ms.Irasha | 2014-08-15 | 2014-08-31
2 | Agree to complete 'Online Leave Application' form on 18th of August. | Mr.Thanuja | 2014-08-15 | 2014-08-18
3 | Agree to complete 'Leave Management' module on 20th of August. | Mr.Anjana | 2014-08-15 | 2014-08-20
4 | Decided to finalize 'Salary Module' by 18th of August. | Mr.Chathura | 2014-08-15 | 2014-08-18
5 | Decided to demonstrate the system functionality to QA Team. | Mr.Thanuja & Mr.Anjana | 2014-08-15 | 2014-08-20
Action Items