## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-07-18 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Mr.Chathura Ms.Shashika , Ms.Irasha, Ms.Dilanthika |  | 1. Review the project plan & schedule. | 1hour
2. Include 'Education Verrification' module to the project & project plan.
|  | Organize the Demonstration |  |  | 3. Decide to finalize the presentaion & fixed the Demonstration date.
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
| 1.include 'Education Verrification' module to the project & project plan. | Mr.Promdya & Mr.Anjana | 2014-07-18 |  |  |  |  | Done.
| 2.Decide to finalize the presentaion & fixed the Demonstration date. | Mr.Anjana | 2014-07-18 | 2014-07-21 |  |  |  | Done.
Action Items