## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 19/06/2014 | Serial Numbers Common CSS Custom CSS Nlog Implementation Dead lines for other documentations : Meeting Minitues Action Items Risk Registry SRS Lesson Learned | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Mr.Chatura , Ms.Shashika , Ms.Irasha, Ms.Dilanthika |  | Agree to maintain common CSS layout for all forms. Use autoincremented number for line_no for 'Department Head' & 'Division Head' tables. Decide to use a common method for information selection in gridviews. Information in gridview is retrieved by clicking on the row. Using select link button or any other button is illiminated. scode is removed from serial table and only intcode is used. Agree to implement Nlog for tracking errors & debugs. Review the project plan & schedule. | 1hour | 26/06/2014
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
| Decide to complete Nlog for employee table. | Mr.Promodaya |  | 24/06/2014
| Decide to discuss riskregistary implementation. |  | 24/06/2014 | 14/07/2014
Action Items