## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-09-19 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Ms.Shashika, Ms.Irasha, Ms.Dilanthika |  | 1.Review the project plan & schedule. | 1hour
2.Decided to disable browser button (Back & Forward)
3.Decided to complete user training within 22/09/2014 - 23/09/2014
4.Decided to complete UAT within 24/09/2014 - 26/09/2014
6.Decided to complete UI fine tuning within 29/09/2014 - 30/09/2014
7.Decided to deploy HRIS on 01/10/2014
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
1 | Decided to disable browser button (Back & Forward) | Mr.Thanuja
2 | Decided to complete user training within 22/09/2014 - 23/09/2014 | Ms.Irasha Ms.Dilanthika
3 | Decided to complete UAT within 26/09/2014 | HR
4 | Decided to complete UI fine tuning within 29/09/2014 - 30/09/2014 | Mr.Anjana Mr.Pramodya Mr.Thanuja
5 | Decided to deploy HRIS on 01/10/2014
Action Items