## Meeting Minutes
Meeting # | Meeting Date | Agenda | Participants | Absent | Key Decisions and Discussion Points | Duration (Hrs) | Next Meeting Date/Time
| 2014-07-29 | Project Progress | Mr.Anjana , Mr.Thanuja , Mr.Pramodaya , Mr.Chathura Ms.Shashika , Ms.Irasha, Ms.Dilanthika |  | 1. Review the project plan & schedule. | 1hour
|  | Testing |  |  | 2. Agreed to finalized & deliver 'User Administration' & 'System Configuration' modules on 1st of August.
3. Agree to complete testing phase 1 of 'Employee Information Management' module on 31st of July.
|  | Project Enhancements |  |  | 4. Decide to design a structure for summarizing.
5. Discus to uniform the messages styles in HRIS.
6. Decide to develop a form to track locations of attendence machines.
Meeting Minutes

## Action Items
Action # | Action Item | Owner | Opened Date | Target Date | Percent Complete | Status | Completion Date | Comments
| 1.Agreed to finalized & deliver 'User Administration' & 'System Configuration' modules on 1st of August. | Ms.Dilanthika & Ms.Irasha | 2014-07-29 | 2014-08-01 |  |  |  | Pending.
| 2.Agree to complete testing phase 1 of 'Employee Information Management' module on 31st of July. | Ms.Dilanthika & Ms.Irasha | 2014-07-29 | 2014-07-31 |  |  | 2014-07-31 | Done.
| 3.Decide to design a structure for summarizing. | Mr.Thanuja | 2014-07-29
| 4.Decide to develop a form to track locations of attendence machines. | Ms.Shashika | 2014-07-29 |  |  |  |  | Done.
Action Items